## PHASE 0: PRE-DEVELOPMENT (Week 0-2)

### Account Setup & Planning

__Week 1: Developer Accounts__

- Register Apple Developer Program ($99/year)

- Visit: [](https://developer.apple.com/programs/)<https://developer.apple.com/programs/>

- Complete enrollment (1-2 days processing)

- Accept agreements

- Register Google Play Developer Console ($25 one-time)

- Visit: [](https://play.google.com/console/signup)<https://play.google.com/console/signup>

- Verify identity

- Accept agreements

- Set up App Store Connect account

- Set up Google Play Console account

__Week 2: Design & Architecture__

- Create mobile UI/UX designs (Figma/Sketch)

- Login/Registration screens

- Chat interface

- Profile screens

- Settings screens

- Subscription screens

- All major flows

- Define technical architecture

- Choose team structure (agency vs contractor vs in-house)

- Set up project management (Jira/Trello/Asana)

---

## 🔧 PHASE 1: PROJECT SETUP (Week 3-4)

### Initialize React Native Project

__Week 3: Base Setup__

```bash

# Install React Native CLI

npm install -g react-native-cli

# Create new project

npx react-native init StarshipPsychicsMobile

cd StarshipPsychicsMobile

# Install core dependencies

npm install @react-navigation/native @react-navigation/stack @react-navigation/bottom-tabs

npm install react-native-screens react-native-safe-area-context

npm install @react-native-firebase/app @react-native-firebase/auth

npm install react-native-iap  # For both Apple & Google payments

npm install @react-native-async-storage/async-storage

npm install axios

npm install react-native-gesture-handler react-native-reanimated

```

__Project Structure:__

```javascript

StarshipPsychicsMobile/

├── src/

│   ├── api/              # API integration (reusable from web)

│   ├── components/       # Reusable UI components

│   ├── screens/          # Screen components

│   ├── navigation/       # Navigation configuration

│   ├── services/         # Business logic services

│   │   ├── auth/         # Authentication

│   │   ├── payments/     # Payment logic

│   │   │   ├── apple.js      # Apple IAP

│   │   │   ├── google.js     # Google Play Billing

│   │   │   └── index.js      # Platform detection

│   │   └── api.js        # API client

│   ├── utils/            # Helper functions (reusable from web)

│   ├── hooks/            # Custom React hooks

│   ├── constants/        # App constants

│   ├── assets/           # Images, fonts

│   └── App.js            # Root component

├── ios/                  # iOS native code

├── android/              # Android native code

└── package.json

```

__Week 4: Configuration__

- Configure Firebase for iOS

- Download GoogleService-Info.plist

- Add to Xcode project

- Configure Firebase for Android

- Download google-services.json

- Add to android/app/

- Set up environment variables

- Configure app icons and splash screens

- Set up error tracking (Firebase Crashlytics)

- Set up analytics (Firebase Analytics)

---

## 💳 PHASE 2: PAYMENT SYSTEM SETUP (Week 5-7)

### Apple In-App Purchase Setup

__Week 5: Apple IAP Configuration__

__In App Store Connect:__

- Create app listing

- Bundle ID: com.starshippsychics.mobile

- App name: Starship Psychics

- Create In-App Purchase products

- Monthly subscription: `monthly_subscription`

- Annual subscription: `annual_subscription`

- Configure subscription groups

- Set pricing for all countries

- Submit products for review

__In Code:__

```javascript

// src/services/payments/apple.js

import RNIap from 'react-native-iap';

const SUBSCRIPTION_SKUS = {

monthly: 'monthly_subscription',

annual: 'annual_subscription'

};

export const initializeAppleIAP = async () => {

try {

await RNIap.initConnection();

await RNIap.flushFailedPurchasesCachedAsPendingAndroid();

} catch (err) {

console.warn('IAP initialization failed', err);

}

};

export const getAppleSubscriptions = async () => {

const subscriptions = await RNIap.getSubscriptions([

SUBSCRIPTION_SKUS.monthly,

SUBSCRIPTION_SKUS.annual

]);

return subscriptions;

};

export const purchaseAppleSubscription = async (sku) => {

const purchase = await RNIap.requestSubscription(sku);

return purchase;

};

export const verifyAppleReceipt = async (receipt) => {

// Send to your backend for verification

const response = await fetch('https://your-api.com/api/iap/apple/verify', {

method: 'POST',

headers: { 'Content-Type': 'application/json' },

body: JSON.stringify({ receipt })

});

return response.json();

};

```

### Google Play Billing Setup

__Week 6: Google Play Configuration__

__In Google Play Console:__

- Create app listing

- Package name: com.starshippsychics.mobile

- App name: Starship Psychics

- Create subscription products

- Monthly subscription: `monthly_subscription`

- Annual subscription: `annual_subscription`

- Set pricing for all countries

- Configure subscription benefits

- Activate products

__In Code:__

```javascript

// src/services/payments/google.js

import RNIap from 'react-native-iap';

const SUBSCRIPTION_SKUS = {

monthly: 'monthly_subscription',

annual: 'annual_subscription'

};

export const initializeGoogleBilling = async () => {

try {

await RNIap.initConnection();

await RNIap.flushFailedPurchasesCachedAsPendingAndroid();

} catch (err) {

console.warn('Billing initialization failed', err);

}

};

export const getGoogleSubscriptions = async () => {

const subscriptions = await RNIap.getSubscriptions([

SUBSCRIPTION_SKUS.monthly,

SUBSCRIPTION_SKUS.annual

]);

return subscriptions;

};

export const purchaseGoogleSubscription = async (sku) => {

const purchase = await RNIap.requestSubscription(sku);

return purchase;

};

export const verifyGooglePurchase = async (purchase) => {

// Send to your backend for verification

const response = await fetch('https://your-api.com/api/iap/google/verify', {

method: 'POST',

headers: { 'Content-Type': 'application/json' },

body: JSON.stringify({ purchase })

});

return response.json();

};

```

__Week 7: Platform-Agnostic Payment Service__

```javascript

// src/services/payments/index.js

import { Platform } from 'react-native';

import * as AppleIAP from './apple';

import * as GoogleBilling from './google';

export const initializePayments = async () => {

if (Platform.OS === 'ios') {

return AppleIAP.initializeAppleIAP();

} else {

return GoogleBilling.initializeGoogleBilling();

}

};

export const getSubscriptionProducts = async () => {

if (Platform.OS === 'ios') {

return AppleIAP.getAppleSubscriptions();

} else {

return GoogleBilling.getGoogleSubscriptions();

}

};

export const purchaseSubscription = async (sku) => {

if (Platform.OS === 'ios') {

return AppleIAP.purchaseAppleSubscription(sku);

} else {

return GoogleBilling.purchaseGoogleSubscription(sku);

}

};

```

---

## 🔐 PHASE 3: BACKEND INTEGRATION (Week 8-9)

### Receipt Verification API

__Week 8: Backend API Endpoints__

Create new API routes in your existing backend:

```javascript

// api/routes/mobile/iap.js

import { Router } from 'express';

import { verifyAppleReceipt } from '../../services/apple-iap';

import { verifyGooglePurchase } from '../../services/google-billing';

const router = Router();

// Apple receipt verification

router.post('/apple/verify', async (req, res) => {

const { receipt, userId } = req.body;

try {

// Verify with Apple servers

const verification = await verifyAppleReceipt(receipt);

if (verification.status === 0) {

// Valid receipt - update user subscription

await db.query(

`UPDATE user_personal_info

SET subscription_status = 'active',

apple_receipt = $1,

subscription_platform = 'apple'

WHERE user_id = $2`,

[receipt, userId]

);

res.json({ success: true, subscription: verification });

} else {

res.status(400).json({ success: false, error: 'Invalid receipt' });

}

} catch (error) {

res.status(500).json({ success: false, error: error.message });

}

});

// Google purchase verification

router.post('/google/verify', async (req, res) => {

const { purchaseToken, productId, userId } = req.body;

try {

// Verify with Google Play API

const verification = await verifyGooglePurchase(purchaseToken, productId);

if (verification.valid) {

// Valid purchase - update user subscription

await db.query(

`UPDATE user_personal_info

SET subscription_status = 'active',

google_purchase_token = $1,

subscription_platform = 'google'

WHERE user_id = $2`,

[purchaseToken, userId]

);

res.json({ success: true, subscription: verification });

} else {

res.status(400).json({ success: false, error: 'Invalid purchase' });

}

} catch (error) {

res.status(500).json({ success: false, error: error.message });

}

});

export default router;

```

__Week 9: Database Schema Updates__

```sql

-- Add mobile payment columns

ALTER TABLE user_personal_info ADD COLUMN IF NOT EXISTS apple_receipt TEXT;

ALTER TABLE user_personal_info ADD COLUMN IF NOT EXISTS google_purchase_token TEXT;

ALTER TABLE user_personal_info ADD COLUMN IF NOT EXISTS subscription_platform VARCHAR(20);

-- Create mobile purchases log table

CREATE TABLE IF NOT EXISTS mobile_purchases (

id SERIAL PRIMARY KEY,

user_id VARCHAR(255) NOT NULL,

platform VARCHAR(20) NOT NULL, -- 'apple' or 'google'

product_id VARCHAR(255) NOT NULL,

transaction_id VARCHAR(255) NOT NULL,

purchase_token TEXT,

receipt TEXT,

purchase_date TIMESTAMP NOT NULL,

expiry_date TIMESTAMP,

is_verified BOOLEAN DEFAULT false,

created_at TIMESTAMP DEFAULT NOW()

);

CREATE INDEX idx_mobile_purchases_user_id ON mobile_purchases(user_id);

CREATE INDEX idx_mobile_purchases_transaction_id ON mobile_purchases(transaction_id);

```

---

## 🎨 PHASE 4: UI DEVELOPMENT (Week 10-16)

### Week 10-11: Authentication Screens

__Screens to Build:__

- Splash Screen

- Landing/Welcome Screen

- Login Screen

- Registration Screen

- Email Verification Screen

- 2FA Setup Screen

- 2FA Verification Screen

- Forgot Password Screen

__Reusable from Web:__

- Authentication logic

- Form validation

- API calls

__Must Build Native:__

- All UI components

- Navigation flows

- Biometric authentication (Face ID/Touch ID)

### Week 12-13: Main Chat Interface

__Screens to Build:__

- Chat Screen (main)

- Message Input Component

- Message Bubble Component

- Typing Indicator

- Chat History List

__Features:__

- Real-time messaging

- Message persistence

- Pull-to-refresh

- Keyboard handling

- Auto-scroll to bottom

- Health content guardrails

### Week 14: User Profile & Settings

__Screens to Build:__

- Profile Screen

- Edit Profile Screen

- Settings Screen

- Preferences Screen

- Security Screen

- Privacy Settings Screen

### Week 15: Subscription Management

__Screens to Build:__

- Subscription Plans Screen

- Purchase Flow Screen

- Subscription Status Screen

- Manage Subscription Screen (deep link to App Store/Play Store)

__Key Components:__

```javascript

// src/screens/SubscriptionScreen.jsx

import React, { useEffect, useState } from 'react';

import { View, Text, Button, ActivityIndicator } from 'react-native';

import { getSubscriptionProducts, purchaseSubscription } from '../services/payments';

export const SubscriptionScreen = () => {

const [products, setProducts] = useState([]);

const [loading, setLoading] = useState(true);

useEffect(() => {

loadProducts();

}, []);

const loadProducts = async () => {

try {

const subs = await getSubscriptionProducts();

setProducts(subs);

} catch (error) {

console.error('Failed to load products', error);

} finally {

setLoading(false);

}

};

const handlePurchase = async (productId) => {

try {

const purchase = await purchaseSubscription(productId);

// Verify with backend

await verifyPurchaseWithBackend(purchase);

// Navigate to success screen

} catch (error) {

console.error('Purchase failed', error);

}

};

if (loading) {

return <ActivityIndicator />;

}

return (

<View>

{products.map(product => (

<View key={product.productId}>

<Text>{product.title}</Text>

<Text>{product.description}</Text>

<Text>{product.localizedPrice}</Text>

<Button

title="Subscribe"

onPress={() => handlePurchase(product.productId)}

/>

</View>

))}

</View>

);

};

```

### Week 16: Astrology Features

__Screens to Build:__

- Horoscope Screen

- Moon Phase Screen

- Birth Chart Screen

- Cosmic Weather Screen

---

## 🔔 PHASE 5: NATIVE FEATURES (Week 17-18)

### Week 17: Push Notifications

__Setup Firebase Cloud Messaging:__

```bash

npm install @react-native-firebase/messaging

```

__iOS Configuration:__

- Enable push notifications in Xcode

- Upload APNs certificate to Firebase

- Request notification permissions

__Android Configuration:__

- Configure Firebase messaging

- Set up notification channels

__Implementation:__

```javascript

// src/services/notifications.js

import messaging from '@react-native-firebase/messaging';

export const requestNotificationPermission = async () => {

const authStatus = await messaging().requestPermission();

return authStatus === messaging.AuthorizationStatus.AUTHORIZED;

};

export const getFCMToken = async () => {

const token = await messaging().getToken();

return token;

};

export const subscribeToTopics = async (topics) => {

for (const topic of topics) {

await messaging().subscribeToTopic(topic);

}

};

```

### Week 18: Additional Native Features

- Biometric Authentication (Face ID / Touch ID)

- Local Storage & Caching

- Deep Linking

- Share Functionality

- Haptic Feedback

- Dark Mode Support

- Localization (i18n)

---

## 🧪 PHASE 6: TESTING (Week 19-20)

### Week 19: Functional Testing

__Test Scenarios:__

- User registration flow

- Login / logout

- Chat functionality

- Subscription purchase (iOS)

- Subscription purchase (Android)

- Payment failure handling

- Offline mode

- Push notifications

- Deep links

- Biometric auth

__Testing Checklist:__

- Test on iPhone (latest iOS)

- Test on iPhone (iOS -1 version)

- Test on Android (latest)

- Test on Android (API 28)

- Test on tablets

- Test with poor network

- Test with no network

- Test memory usage

- Test battery impact

### Week 20: Beta Testing

__iOS TestFlight:__

- Create TestFlight beta group

- Upload beta build

- Invite 25-50 testers

- Collect feedback

- Fix critical bugs

__Android Internal Testing:__

- Create internal test track

- Upload APK/AAB

- Invite testers

- Collect feedback

- Fix critical bugs

---

## 📱 PHASE 7: APP STORE PREPARATION (Week 21-22)

### Week 21: iOS App Store

__Required Assets:__

- App Icon (1024x1024)

- Screenshots (6.7", 6.5", 5.5")

- At least 3 screenshots per size

- Show key features

- App Preview video (optional but recommended)

- Privacy Policy URL

- Support URL

- Marketing URL (optional)

__App Store Connect Configuration:__

- App name: Starship Psychics

- Subtitle (30 chars)

- Description (4000 chars max)

- Keywords (100 chars, comma-separated)

- Category: Lifestyle > Entertainment

- Age rating: 12+ (spiritual content)

- Privacy details (data collection disclosure)

- App Review Information

- Demo account credentials

- Contact information

- Notes for reviewer

__Privacy Manifest (Required):__ Create `PrivacyInfo.xcprivacy` in Xcode with:

- Data types collected

- Tracking domains

- Required reason APIs

### Week 22: Google Play Store

__Required Assets:__

- App Icon (512x512)

- Feature Graphic (1024x500)

- Screenshots (minimum 2, maximum 8)

- Phone screenshots

- Tablet screenshots (if supporting tablets)

- Promo video URL (YouTube)

- Privacy Policy URL

__Play Console Configuration:__

- App name: Starship Psychics

- Short description (80 chars)

- Full description (4000 chars max)

- Category: Lifestyle

- Content rating: ESRB rating

- Target audience

- Data safety section

- Data collected

- Data sharing

- Security practices

- App content declarations

- Ads (yes/no)

- In-app purchases (yes)

- Content rating questionnaire

---

## 🚀 PHASE 8: SUBMISSION & LAUNCH (Week 23-24)

### Week 23: Submit for Review

__iOS Submission:__

```bash

# Build release version

cd ios

xcodebuild -workspace StarshipPsychicsMobile.xcworkspace \

-scheme StarshipPsychicsMobile \

-configuration Release \

archive -archivePath build/StarshipPsychicsMobile.xcarchive

# Upload to App Store Connect

xcodebuild -exportArchive \

-archivePath build/StarshipPsychicsMobile.xcarchive \

-exportPath build \

-exportOptionsPlist exportOptions.plist

```

__Or use Xcode:__

- Product > Archive

- Distribute App > App Store Connect

- Upload

__Android Submission:__

```bash

# Generate signed AAB

cd android

./gradlew bundleRelease

# Output: android/app/build/outputs/bundle/release/app-release.aab

```

__Upload to Play Console:__

- Create new release

- Upload AAB file

- Review release details

- Submit for review

### Week 24: Monitor & Launch

__iOS Review (1-7 days):__

- Monitor App Store Connect for status

- Respond to any rejection feedback immediately

- Resubmit if necessary

- Once approved, release app

__Android Review (1-3 days):__

- Monitor Play Console for status

- Usually faster approval

- Address any policy violations

- Once approved, publish

__Post-Launch:__

- Monitor crash reports (Firebase Crashlytics)

- Monitor user reviews

- Track key metrics (downloads, DAU, retention)

- Respond to user feedback

- Plan first update

---

## 💰 SUBSCRIPTION COMMISSION STRUCTURE

### Apple App Store

- __First Year:__ 30% commission

- __After Year 1:__ 15% commission (for retained subscribers)

- __Small Business Program:__ 15% if under $1M annual revenue

### Google Play Store

- __First $1M:__ 15% commission

- __After $1M:__ 30% commission

- __Better than Apple for small businesses__

### Revenue Example

If user pays $9.99/month:

- __Apple (Year 1):__ You get $6.99, Apple gets $3.00

- __Apple (Year 2+):__ You get $8.49, Apple gets $1.50

- __Google:__ You get $8.49, Google gets $1.50

---

## 🔒 SECURITY & COMPLIANCE

### Required Implementations

- Secure storage for auth tokens (Keychain/Keystore)

- SSL pinning for API calls

- Receipt validation on server-side

- GDPR compliance (data deletion, export)

- CCPA compliance (California users)

- Encryption for sensitive data

- Secure handling of payment info

- Privacy policy updates for mobile

- Terms of service updates

---

## 📊 SUCCESS METRICS TO TRACK

### Key Performance Indicators

- __Downloads:__ Target 10,000+ in first 3 months

- __Conversion Rate:__ 5-10% of downloads to paid subscribers

- __Retention:__ 40% Day 7, 20% Day 30

- __Crash-Free Rate:__ >99.5%

- __App Store Rating:__ >4.0 stars

- __Customer Lifetime Value (LTV):__ Track monthly

- __Churn Rate:__ <10% monthly

---

## 🐛 TROUBLESHOOTING COMMON ISSUES

### iOS Issues

__Problem:__ Build fails with "Code signing error" __Solution:__ Regenerate certificates and provisioning profiles

__Problem:__ IAP not working in TestFlight __Solution:__ Ensure IAP products are approved in App Store Connect

__Problem:__ App rejected for "Guideline 4.2 - Minimum Functionality" __Solution:__ Add more unique value, ensure native feel

### Android Issues

__Problem:__ Google Play Billing not connecting __Solution:__ Ensure app is uploaded to Play Console (billing only works with uploaded apps)

__Problem:__ Build fails with "Duplicate class" __Solution:__ Check for conflicting dependencies in build.gradle

---

## 📚 RESOURCES & DOCUMENTATION

### Official Documentation

- React Native: [](https://reactnative.dev/docs/getting-started)<https://reactnative.dev/docs/getting-started>

- Apple IAP: [](https://developer.apple.com/in-app-purchase/)<https://developer.apple.com/in-app-purchase/>

- Google Play Billing: [](https://developer.android.com/google/play/billing)<https://developer.android.com/google/play/billing>

- react-native-iap: [](https://github.com/dooboolab/react-native-iap)<https://github.com/dooboolab/react-native-iap>

### Tools

- __App Store Connect:__ [](https://appstoreconnect.apple.com)<https://appstoreconnect.apple.com>

- __Google Play Console:__ [](https://play.google.com/console)<https://play.google.com/console>

- __Firebase Console:__ [](https://console.firebase.google.com)<https://console.firebase.google.com>

- __TestFlight:__ Built into App Store Connect

- __Android Internal Testing:__ Built into Play Console

---

## ⚡ QUICK START CHECKLIST

- Register Apple Developer account ($99/year)

- Register Google Play Developer account ($25 one-time)

- Decide on team structure (agency/contractor/in-house)

- Create mobile UI designs

- Initialize React Native project

- Set up Firebase for both platforms

- Configure payment products in both stores

- Build authentication flow

- Build chat interface

- Implement payment system

- Add push notifications

- Beta test with TestFlight & Play Console

- Create app store assets

- Submit for review

- Launch! 🚀

---

## 💡 FINAL RECOMMENDATIONS

1. __Start with Android first__ - Faster approval, easier testing, lower commission (15% vs 30%)

2. __Use TypeScript__ - Better code quality and fewer bugs

3. __Implement analytics early__ - Firebase Analytics or Amplitude

4. __Plan for iteration__ - First version won't be perfect

5. __Budget for maintenance__ - 20% of development cost annually

6. __Consider hiring specialists__ - IAP implementation is complex

7. __Test on real devices__ - Simulators hide real issues

8. __Prepare for rejection__ - Apple rejects ~40% of initial submissions

9. __Monitor user feedback__ - Respond quickly to reviews

10. __Plan updates__ - Release updates every 2-4 weeks initially

---

## 🎯 YOUR NEXT 3 STEPS

1. __Register developer accounts__ (Apple & Google) - Do this TODAY

2. __Choose your team__ (agency vs contractor) - This week

3. __Create mobile designs__ (Figma/Sketch) - Next 2 weeks

Once those are done, you're ready to start development!

---

__Questions? Need clarification on any phase? Let me know and I can dive deeper into specific areas!__

**